## Stripboard
NIGHT SHIFT FILM PRODUCTION CONTROL BOOK
Stripboard with labeled shoot-date grid and colored scene schedule blocks
Day | Scene | Location | Cast | D/N | Pages | 15 Mar | 16 Mar | 17 Mar | 18 Mar | 19 Mar | 20 Mar | 21 Mar | 22 Mar | 23 Mar | Status
1 | 3A | Diner exterior | A,B | N | 1.5 | ■ | ■ | [7 empty] | Ready
1 | 4 | Diner interior | A,B,C | N | 3 |  | ■ | ■ | [6 empty] | Ready
2 | 7 | Alley rain | B,D | N | 2.25 |  |  | ■ | ■ | [5 empty] | Prep
3 | 9 | Rooftop | A,D | N | 1.75 |  |  |  | ■ | ■ |  |  |  |  | Hold
4 | 12 | Apartment | C | D | 2 |  |  |  |  | ■ | ■ |  |  |  | Ready
5 | 15 | Hospital | A,E | D | 2.5 | [5 empty] | ■ | ■ |  |  | Prep
6 | 18 | Bridge | A,B,D | N | 1 | [6 empty] | ■ | ■ | ■ | Ready
7 | 21 | Warehouse | All | N | 4 | [7 empty] | ■ | ■ | ■

## Shoot Days
Date | Unit | Scenes | Page Count | Company Move | Completion
2026-04-03 | Main | 2 | 4.5 | TRUE | 0.75
2026-04-04 | Main | 1 | 2.25 | FALSE | 0.375
2026-04-05 | Main | 1 | 1.75 | TRUE | 0.29167
2026-04-06 | Main | 1 | 2 | FALSE | 0.33333
2026-04-07 | Main | 1 | 2.5 | TRUE | 0.41667

## Budget
Category | Budget | Actual | Variance
Crew | 42000 | 44500 | -2500
Locations | 18000 | 16500 | 1500
Equipment | 26000 | 27400 | -1400
Post | 15000 | 13800 | 1200
Contingency | 9000 | 7000 | 2000

## Call Sheet
Role | Name | Call Time | Location | Phone
Director | Mara Ellison | 17:00 | Diner | 555-0101
DP | Quinn Vale | 17:30 | Diner | 555-0122
1st AD | Jon Park | 16:30 | Basecamp | 555-0191

## Risks
Risk | Probability | Impact | Mitigation
Rain exterior | 0.45 | 4 | Cover set
Permit delay | 0.25 | 5 | Backup alley
Overtime | 0.35 | 3 | Prelight