## Projects
Relay Project Portfolio — Source Register
Editable project data drives the risk map, KPI totals, and milestone register.
Project | Portfolio | Owner | Budget | Impact | Risk | Health | Progress | Next milestone | Milestone | Risk load
Identity migration | Platform | Hana | 210000 | 5 | 4 | At risk | 71% | 2026-11-12 | Security sign-off | 840000
Warehouse automation | Operations | Victor | 145000 | 5 | 3 | On track | 46% | 2026-12-03 | Pilot launch | 435000
EU market entry | Growth | Nadia | 85000 | 4 | 4 | At risk | 32% | 2026-12-18 | Legal entity | 340000
New help center | Customer | Leo | 42000 | 3 | 2 | On track | 88% | 2026-10-28 | Content freeze | 84000
Analytics rebuild | Platform | Grace | 176000 | 4 | 5 | Paused | 63% | 2027-01-10 | Data contract | 880000
Partner portal | Growth | Owen | 93000 | 3 | 3 | Planning | 25% | 2027-01-22 | Prototype review | 279000
Support routing | Customer | Leo | 54000 | 4 | 2 | On track | 79% | 2026-11-08 | Queue migration | 108000
SOC 2 readiness | Operations | Hana | 118000 | 5 | 5 | At risk | 57% | 2026-12-30 | Evidence audit | 590000

## Portfolio Map
Relay Project Portfolio Command
RISK × IMPACT MAP · EXECUTIVE PRIORITIES, INVESTMENT, PROGRESS, AND NEXT MILESTONES
TOTAL INVESTMENT | AT RISK |  | AVG PROGRESS |  | HIGH-RISK LOAD |  |  | STEERING CALL Identity + SOC 2 need executive unblock; pause Analytics until data ownership is signed.
923000 | 3 |  | 57.63% |  | 589000
PORTFOLIO RISK × IMPACT MAP |  |  |  | NEXT MILESTONES
PROTECT THE BETS |  | CONTROL EXPOSURE |  | Project | Owner | Health | Progress | Date | Milestone | Budget
Identity migration |  | Analytics rebuild |  | Identity migration | Hana | At risk | 71% | 2026-11-12 | Security sign-off | 210000
EU market entry |  | Partner portal |  | Warehouse automation | Victor | On track | 46% | 2026-12-03 | Pilot launch | 145000
SOC 2 readiness |  |  |  | EU market entry | Nadia | At risk | 32% | 2026-12-18 | Legal entity | 85000
|  |  |  | New help center | Leo | On track | 88% | 2026-10-28 | Content freeze | 42000
ACCELERATE |  | MAINTAIN |  | Analytics rebuild | Grace | Paused | 63% | 2027-01-10 | Data contract | 176000
Warehouse automation |  | New help center |  | Partner portal | Owen | Planning | 25% | 2027-01-22 | Prototype review | 93000
Support routing |  |  |  | Support routing | Leo | On track | 79% | 2026-11-08 | Queue migration | 54000
|  |  |  | SOC 2 readiness | Hana | At risk | 57% | 2026-12-30 | Evidence audit | 118000
Map reading · Top-left = high impact / high risk. Investment decisions live in Projects; this page is the leadership conversation.