## Run of Show
Willow & Rose Wedding Run-of-Show
Time | Moment | Owner | Location | Dependency
9:00 | Load-in begins | Planner | Orchard lawn | Venue open
11:30 | Florals placed | Florist | Ceremony arch | Tables set
14:00 | Wedding party photos | Photographer | Rose garden | Hair complete
16:30 | Ceremony | Officiant | Lawn | Guests seated
17:15 | Cocktail hour | Catering lead | Terrace | Bar open
18:30 | Dinner service | Banquet captain | Hall | Grand entrance
20:00 | First dance | DJ | Hall | Dessert staged
22:45 | Send-off | Planner | Front drive | Cars ready

## Vendor Payments
Vendor | Due Date | Amount | Paid | Progress | Status
Evergreen Florals | 2026-09-01 | 4200 | 2100
Lark Catering | 2026-09-10 | 12800 | 6400
Rosewood Quartet | 2026-09-15 | 1800 | 1800
Formulas:
Status = IF([Progress]=1,"Paid",IF([Due Date]<TODAY(),"Due now","Scheduled"))

## Guest Logistics
Group | Count | Transport | Notes
Family | 38 | Shuttle A | Front rows
Friends | 72 | Rideshare | Terrace entry
Vendors | 18 | Service lot | Meal tickets

## Checklist
Task | Owner | Due | Done
Rings to best man | Planner | 2026-09-19
Final headcount | Couple | 2026-09-10
Vendor meals | Caterer | 2026-09-18