August 5, 2026

Jordan Lee
Program Director
Nova Civic Lab
88 Union Avenue · Portland, OR 97204

Dear Jordan,

Thank you for the thoughtful discussion about a six-week shade-mapping pilot for the East Junction district.

The proposed pilot would combine three field observation corridors, a shared evidence log, and a concise findings brief for district partners. To keep momentum, we suggest the following sequence:

Confirm the three observation corridors and data-sharing contact by August 14.

Hold a 45-minute field-method review during the week of August 17.

Begin resident observations on August 24, subject to weather and access.

If this outline matches your expectations, please reply with the project contact and two preferred review times. We would be glad to circulate a short work plan before the meeting.

Sincerely,

Mara Ellison

Principal · Alder Field Studio